## Burn down chart
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 64 | 64
1 | 44 | 45
2 | 0
Link to Sprint tasks
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
35 | 20 | 20 | 2018-08-17
34 | 19 | 20 | 2018-08-18
33 | 19 | 20 | 2018-08-19
32 | 18 | 20 | 2018-08-20
31 | 18 | 20 | 2018-08-21
30 | 17 | 20 | 2018-08-22
29 | 17 | 20 | 2018-08-23
28 | 16 | 20 | 2018-08-24
27 | 15 | 20 | 2018-08-25
26 | 15 | 20 | 2018-08-26
25 | 14 | 20 | 2018-08-27
24 | 14 | 20 | 2018-08-28
23 | 13 | 20 | 2018-08-29
22 | 13 | 20 | 2018-08-30
21 | 12 | 19.2 | 2018-08-31
20 | 11 | 19.2 | 2018-09-01
19 | 11 | 18.8 | 2018-09-02
18 | 10 | 18.8 | 2018-09-03
17 | 10 | 16.8 | 2018-09-04
16 | 9 | 16.8 | 2018-09-05
15 | 9 | 14.8 | 2018-09-06
14 | 8 | 14.8 | 2018-09-07
13 | 7 | 14.8 | 2018-09-08
12 | 7 | 14.8 | 2018-09-09
11 | 6 | 13.2 | 2018-09-10
10 | 6 | 11.2 | 2018-09-11
9 | 5 | 9.2 | 2018-09-12
8 | 5 | 9.2 | 2018-09-13
7 | 4 | 9.2 | 2018-09-14
6 | 3 | 9.2 | 2018-09-15
5 | 3 | 9.2 | 2018-09-16
4 | 2 | 9.2 | 2018-09-17
3 | 2 | 9.2 | 2018-09-18
2 | 1 | 3 | 2018-09-19
1 | 1 | 3 | 2018-09-20
0 | 0 | 1 | 2018-09-21
Sprint 2 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
25 | 45 | 45 | 2018-10-01
24 | 43 | 45 | 2018-10-02
23 | 41 | 45 | 2018-10-03
22 | 40 | 45 | 2018-10-04
21 | 38 | 45 | 2018-10-05
20 | 36 | 45 | 2018-10-06
19 | 34 | 45 | 2018-10-07
18 | 32 | 45 | 2018-10-08
17 | 31 | 45 | 2018-10-09
16 | 29 | 45 | 2018-10-10
15 | 27 | 45 | 2018-10-11
14 | 25 | 45 | 2018-10-12
13 | 23 | 45 | 2018-10-13
12 | 22 | 45 | 2018-10-14
11 | 20 | 45 | 2018-10-15
10 | 18 | 45 | 2018-10-16
9 | 16 | 45 | 2018-10-17
8 | 14 | 45 | 2018-10-18
7 | 13 | 45 | 2018-10-19
6 | 11 | 45 | 2018-10-20
5 | 9 | 45 | 2018-10-21
4 | 7 | 45 | 2018-10-22
3 | 5 | 45 | 2018-10-23
2 | 4 | 45 | 2018-10-24
1 | 2 | 45 | 2018-10-25
0 | 0 | 45 | 2018-10-26

## Sprint Tasks
Story 01: Creating new account
Task ID | Task Description | Estimate | Taken | Actual Taken
1 | Create new account page | 1 |  | done 13/09 | 1
2 | Implementing code for verifying fields | 1 |  | done 13/09 | 1
3 | Adding account to database | 1
4 | Verify story is complete (acceptance test) | 1
| Story Points: 4 Total Hours: | 4
Story 02: Different levels of authorisation/login (Access to role-specific features)
Task ID | Task Description | Estimate | Taken | Actual Taken
1 | Create login page | 1 |  | done 31/08 | 0.8
2 | Implementing code for verifying fields + checking if account exists | 1 |  | done 10/09 | 0.8
3 | Logging in as respected used based on login details | 1 |  | done 10/09 | 0.8
4 | Implementing code for hiding/showing features on pages based on level of authentication | 2
5 | Verify story is complete (acceptance test) | 1
| Story Points: 4 Total Hours: | 6
Story 03: Search Function
Task ID | Task Description | Estimate | Taken | Actual Taken
1 | Migrating database to the web server | 2 |  | half done 4/09 | 2
2 | Implementing code for search query that goes through each item in database | 4 |  | done 11/09 | 2
3 | Displaying items on webpage that matches the query | 2 |  | done 6/09 | 2
4 | Verify story is complete (acceptance test) | 1
| Story Points: 8 Total Hours: | 9
Story 04: Vehicle status and store location
Task ID | Task Description | Estimate | Taken | Actual Taken
1 | Migrating database to the web server | 2
2 | Displaying vehicle status on search-list page/individual vehicle page | 2
3 | Verify story is complete (acceptance test) | 1
| Story Points: 2 Total Hours: | 5
Story 05: Online vehicle reservation
Task ID | Task Description | Estimate | Taken | Actual Taken
1 | Create reservation page | 1 |  | done 2/09 | 0.4
2 | Implementing code for booking/reserving a vehicle | 2
3 | Updating vehicle status in database | 1
4 | Displaying new status of vehicles on search-list page/individual vehicle page | 1
5 | Verify story is complete (acceptance test) | 1
| Story Points: 2 Total Hours: | 6
|  |  |  | Total Done | 10.8